## Sheet1
| June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Planning | bar: June W3
Requirements gathering and Analysis | bar: June W4
System design | bar: June W4 to July W1
Preparation for initial deliverables | bar: July W1
Submission of chapter 2 & 3 | bar: July W2
Submission of Objectives/SOP | bar: July W3
Submission of chapter 4 | bar: July W4
Submission of Appendices & CV | bar: August W1
preparation of deliverables to be submitted | bar: August W2
Submission of Abstract & Chapter 1 | bar: August W2
Proposal Document draft | bar: August W3
Rebriefing with the group | bar: August W4
Submission of draft capstone proposal | bar: September W1
Submission of Capstone proposal w/ endorsment letter | bar: September W2
Submission of rubric | bar: September W3
Capstone Proposal defense | bar: September W4
Submission of revised capstone document | bar: October W1
Coding user Side | bar: October W2 to November W2
Coding Admin Side | bar: October W3 to December W3
Coding Crew Side | bar: October W2 to January W2
Implementation | bar: October W2 to January W2
Code Testing | bar: December W4 to February W1
Company testing with the system | bar: December W4 to February W1
Coding Tracking application | bar: November W4 to January W2
testing tracking application | bar: December W4 to February W1